## Log
Steady State Readiness Assessment Utility
Document Revision History
Ver # | Date | Author | Reviewer | Comments
Draft | Jun, 2017 | Subrato |  | initial version
V1 | Jul, 2017 |  | Komal | Framework review & updates
V2 | 2017-07-14 | Subrato |  | incorporated miscellaneous comments
V3 | 2019-03-14 | Siva |  | Customized for Verizon ADM program

## Help (hidden)
How DRM anchor can use this tool?
Only cells in white / no highlight need to be updated
Color coded cells are colored formulaically
Need to update [Readiness Parm Details] first - update "Weightage" and "Readiness" columns. In case an activity is 'Not applicable', update 'NA' for both weightage and readiness
In [Readiness summary] - DRM remarks column with risk areas need to be updated

## Legend
* Valid for individual tracks
Legend |  |  |  | Weightage factor
Color Code | Readiness threshold (%) | Lower range | Median value | Weightage | Keyword | Factor
Red | 75% | 0% | 37.5% | NA | NA | 0
Amber | 85% | 75% | 80% | default weightage | default | 1
Yellow | 98% | 85% | 91.5% | multiplier weightage | increased | 3
Green | 100% | 98% | 99% | escalated weightage | escalated | 5
NA | 100% | 0% | 50%
Weightage applicability - weightage needs to be applied based on how critical is the activity
Readiness color - this needs to be populated based on the current status of an activity

## Readiness Parm Details
DRM Anchor to update column D & F as per program assessment.
Oracle Grid and SQL Server Grid
# | Tracks | Activities / Milestone checkpoints | Weightage applicability | Weightage factor | Readiness Color | Readiness quotient (%) | Total tasks weightage | Track score
1 | Setup, Connectivity | Connectivity, ports access obtained | default | 1 | Green | 99% | 15 | 99%
2 |  | access approval to offshore for applications | NA | 1 | Green | 99%
3 |  | access, logins to applications, servers etc | default | 1 | Green | 99%
4 |  | Access matrix and audit logs (who needs to have what level of access) | default | 1 | Green | 99%
5 |  | Environments (Online environments i.e. test, quality assurance, pilot, pre-production & production, Batch environments) | default | 1 | Green | 99%
6 |  | Configuration control (Key interfaces in and out of the application including program details, , Source code location, Database detail location) | default | 1 | Green | 99%
7 |  | Communication plan, SPOC / contact points | default | 1 | Green | 99%
8 |  | Governance Structure, escalation matrix | default | 1 | Green | 99%
9 |  | ODC / seating arrangement, transport logistics | NA | 0 | NA | 50%
10 |  | ODC restriction handling readiness - e.g., min 4 people ODC | NA | 0 | NA | 50%
11 |  | Staffing, process - background check, on-boarding flow | default | 1 | Green | 99%
12 |  | Shift roster, leave plan (including on-call requirements and obtain pagers/cell phones) | default | 1 | Green | 99%
13 |  | shift handover process | default | 1 | Green | 99%
14 |  | vendor agreements if any | NA | 0 | NA | 50%
15 |  | re-badged employee contracts | default | 1 | Green | 99%
16 |  | S/W licenses | default | 1 | Green | 99%
17 |  | Hardware (i.e. servers, workstations, printers etc) availability Disaster recovery | default | 1 | Green | 99%
18 |  | Training | default | 1 | Green | 99%
19 | Transition / Transformation | Knowledge Transfer (KT) acceptance signoff | default | 1 | Green | 99% | 10 | 98.25%
20 |  | Reverse Knowledge Transfer (RKT) acceptance signoff | NA | 0 | NA | 50%
21 |  | Documentation (Document Repository Setup Signed Off. All documents should be at one central location and SME need to signoff on the same.) | default | 1 | Green | 99%
22 |  | Acceptance of deliverables during KT (such as System Appreciation document) | NA | 0 | NA | 50%
23 |  | Secondary Support acceptance signoff | default | 1 | Green | 99%
24 |  | Technical Recovery, Disaster Recovery procedures executed by the team. (KT is complete and all documents are available related to the same in document repository under separate folder) | default | 1 | Green | 99%
25 |  | Standard Operating Procudure defined | default | 1 | Green | 99%
26 |  | scehduled and batch processes | default | 1 | Green | 99%
27 |  | 3rd party dependences (including process/Procedures for interacting with all third party vendors defined) | NA | 0 | NA | 50%
28 |  | Incidents exceptions identified | NA | 0 | NA | 50%
29 |  | Incidents backlog handling plan agreed with customer | default | 1 | Green | 99%
30 |  | Scope agreement | default | 1 | Green | 99%
31 |  | Procedure for interaction with business / client has been finalized and agreed | default | 1 | Green | 99%
32 |  | NIA automations - readiness | NA | 0 | NA | 50%
33 |  | Readiness for SOX/UAR/SOD needs identified and tracked (If the owner is Infosys then KT to be done and processes are to be documented) | default |  | Green
34 |  | Readiness on security maven roles at application level (If the owner is Infosys then KT to be done and processes are to be documented) | default |  | Green
35 |  | Contractual awareness - SLA, penalty, exclusion clauses, impact due to 3rd party | default | 1 | Yellow | 91.5%
36 | Support | Fixed defects / incidents of all severities (as per targets agreed in Secondary Support Acceptance) [Serv1, Serv2, P1, P2,etc] | default | 1 | Green | 99% | 9 | 99%
37 |  | Fixed defects / incidents of all severities (as per targets agreed in Secondary Support Acceptance) [ End-Of-Period processes , Ad-hoc requests, Routine jobs / processes ] | default | 1 | Green | 99%
38 |  | Fixed defects / incidents of all severities (as per targets agreed in Primary Support Acceptance) [Serv1, Serv2, P1, P2,etc] | default | 1 | Green | 99%
39 |  | Fixed defects / incidents of all severities (as per targets agreed in Primary Support Acceptance) [Serv4, P3, P4,etc] | default | 1 | Green | 99%
40 |  | Fixed defects / incidents of all severities (as per targets agreed in Priamry Support Acceptance) [ End-Of-Period processes , Ad-hoc requests, Routine jobs / processes ] | default | 1 | Green | 99%
41 |  | Familiar with a Service Management Tool usage - Team has Tracked & Resolved incidents, problems and ad-hoc requests using Service Management Tool (incident logging, updating and closure) | default | 1 | Green | 99%
42 |  | Team has used a Test Management Tool for Defect logging, Defect status updates and Defect closure | NA | 0 | NA | 50%
43 |  | Independent resolution and handling of incidence (as part of primary support) | default | 1 | Green | 99%
44 |  | Team has done code promotion / deployment from support environment to production (code check-in, check-out, build and coordination with other groups) | NA | 0 | NA | 50%
45 |  | Application restart activities procedure defined and the activitieshave been performed by the team (for all applications) | default | 1 | Green | 99%
46 |  | Team has resolved incidents involving 3rd party vendor interaction OR process for interacting with 3rd party has been understood from the incumbent team | NA | 0 | NA | 50%
47 |  | Infosys team has taken up the role of Change Coordinator | default | 1 | Green | 99%
48 | Configuration and setup - ITSM, etc | Ticketing Tool setup - access | default | 1 | Green | 99% | 9 | 97.33%
49 |  | Configuration of ticketing tool | default | 1 | Green | 99%
50 |  | Problem tickets classification | default | 1 | Green | 99%
51 |  | Routing of incidents | default | 1 | Green | 99%
52 |  | User groups & access to email group | default | 1 | Green | 99%
53 |  | SLA reports, dashboard configuration (reporting procedure & template agreed) | default | 1 | Yellow | 91.5%
54 |  | SLA exceptions, exclusions | default | 1 | Yellow | 91.5%
55 |  | Incident management process definition | default | 1 | Green | 99%
56 |  | Team's awareness on ticketing tool & SLAs | default | 1 | Green | 99%
57 | Client Agreement | Client Confidence | default | 1 | Green | 99% | 8 | 97.12%
58 |  | Business / Client organization informed of support contacts | default | 1 | Green | 99%
59 |  | Escalation procedure and contacts finalized and shared with the stakeholders | default | 1 | Green | 99%
60 |  | Transition signoff | NA | 0 | NA | 50%
61 |  | Invoicing | NA | 0 | NA | 50%
62 |  | CSG feedback | default | 1 | Green | 99%
63 |  | 3rd Party Vendors informed of support contacts | NA | 0 | NA | 50%
64 |  | Dependencies on Incumbent vendor | NA | 0 | NA | 50%
65 |  | Contractual commitments - acceptance criteria met | default | 1 | Green | 99%
66 |  | Status Reporting - Templates and process defined & agreed | default | 1 | Green | 99%
67 |  | all Transition milestones billed | NA | 0 | NA | 50%
68 |  | sign-off on key transition deliverables | NA | 0 | NA | 50%
69 |  | SLA performance during baseline period | default | 1 | Yellow | 91.5%
70 |  | SLA Targets sign-off | default | 1 | Yellow | 91.5%
| Misc |  |  | #N/A |  | #N/A
| Overall | Overall Score |  | 51 |  | 98.26% | 51 | 98.26%

## Readiness Summary
Update column F to support the reason for RAG status in column E.
| Tracks | Examples - Activities / Milestone checkpoints | Composite Readiness Score | Cardinal Status - by completion % | Remarks
| Setup, Connectivity | Connectivity, ports, access, logins. Environments, Configuration control, Communication plan, escalation matrix, etc Staffing, rosters | 99% | Green
| Transition / Transformation | KT, RKT, documentation, acceptance, Secondary Support, SOPs, scehduled and batch processes, 3rd party dependences, ticketing exceptions identified. Backlog handling plan agreed, Disaster Recovery | 98.25% | Green
| Support | Primary Support clearance - defects / problems / tickets, independent resolution and handling, application restart | 99% | Green
| Configuration and setup - ITSM, etc | ticketing Tool setup - access, configuration, problem clusters, routing, user groups, SLA reports | 97.33% | Yellow | Evaluating/Working through the AYS ticketing system to obtained required reporting to baseline SLA. Currently limited on reporting capabilities. Date of completion end of July.
| Client Agreement | Client perspective, client confidence, signoff, invoicing, feedback, dependencies, SLA Metrics | 97.12% | Yellow | Evaluating/Working through the AYS ticketing system to obtained required reporting to baseline SLA. Currently limited on reporting capabilities. Date of completion end of July.
| Overall | Overall Steady State Readiness Score | 98.26% | Yellow | The above "Cardinal Status" values would all need to be GREEN to have Overall be GREEN