## Slide 1: The Release Plan
Introduction
  Purpose:
    Provide communication to stakeholders throughout the project cycle as the project team continues to respond to feedback from business/Product Owner
    The goal is to communicate a detailed view of features/functions
    The intent is to maintain a collaborative effort that keeps the process more transparent
  Ownership:
    The Agile Project Lead is responsible for creating and maintaining the Release Plan in collaboration with the project team as the project progresses through completion

## Slide 2: The Release Plan
Maintenance
  Start and complete this document during Iteration 0 for the first Release
  Review and update the document after every Iteration planning session, as required
  Changes to the Vision and Roadmap may also be necessary to ensure they remain consistent with this Release Plan

## Slide 3: The Release Plan
Instructions
  Create a copy of this template to use as your Release Plan document
  Delete the first three slides: (Introduction, Maintenance, Instructions)
  Replace the [bracketed] items on each page with information from your project
  Include your document version number in the footer
  Additional instructions and guidance can be found in the Notes section of the individual slides. (Optionally, the notes may be deleted to make room for talking points specific to your project)
  When needed, copy and insert a ‘pre-formatted’ slide into the presentation if an additional page is needed to communicate an overflow of information

## Slide 4: SSM SDFCS
Release 1B
Revision 1.1
3/1/2013
Wajahath Quraishi, Agile Project Lead

## Slide 5: Objectives
Projected Scope:
Timeline
  Release Completion Date: July 25th
  Production Release Date: July 25th
  Iteration Length: 2 weeks
Key Features
Accommodate and process Same Day Standby data in SSM - (SDS)
Accommodate and process Alternate Standby data in SSM -(AS)
Accommodate and process Alternate Flight Change in SSM - (AFC) Accommodate and process Alternate Flight Change First Class in SSM-(AFCF)

## Slide 6: Business Readiness Activities
Key Business project milestones to ensure product success
  Provide the SDS, SDFC, AS, AFC and AFCS products from the Catalog

## Slide 7: Business Case
The features in this Release will help to realize these business benefits:
  Revenue Generation: [details]
  Cost Savings: [details]
  Other Benefits: [details]

## Slide 8: Delivery Plan: page 1 of [N]
 | Iteration 16 | Iteration 17 | Iteration 18
 | [02/26] – [03/11] | [03/12] – [03/25] | [03/26] – [04/08]
Velocity | 18 Points [actual] points | 7 [actual] points | 7 [actual] points
Scope | 106495 - Split PNR for SDS - 3Points 72554 - Process SDS payment thru iTKTs - 3 Points 71025 - Offer SDS payments out of Caribbean and fulfillment thru iTKTs - 3 Points 104754 Process SDFC payment and fulfillment thru iTKTs for Gateside (non elites) - 3 Points 55184 -Standby receipt for SSM - 3 Points 72553 -Print one SDS per customer/transaction - 3 Points [user story not completed in iteration] | 106612 shop for SDS on Gateside and fulfillment for non elites - 3 Points 100759 Customer shop for AS - 2 Points 100756 AS Standby Popup – 2 Points | 12305 Offer Alternate standby out of Caribbean (elite) - 2 102316 :Offerings & Fulfillment: Display alternate flights on – 2 Points Gateside and Payment fulfillment AFC (elite) - 3 Points
Issues | Detailed covered in issue Mgmt. | PVC information from iTKTs | […]
Architecture Decisions | […] | […] | […]
Dependencies | [Due to …] [Due from…] | [Due to …] [Due from…] | [Due to …] [Due from…]
Business Decisions/Impacts | […] | […] | […]
Notes: Since a release plan exists for each release, the number the iterations will be for the release, so X=first iteration number for this release.
As you begin each iteration, verify the previous iterations details are updated to reflect the iteration outcome and then note the new iterations plan. This document replaces your Project Management plan and will serve as a primary communication vehicle for your project. The information on this slide can be copied into the Steering Committee Update Template as your project progresses.
Velocity: Should show values for both planned and actual amounts of work delivered.
Scope: Will show the stories scheduled to be delivered within the iteration. When updating based on actual results, indicate any user stories that were not completed by formatting the story name in italics. These stories should then appear again in the iteration where they will be complete.
Issues: Should reflect those issues that were a significant block for the team during the iteration
Dependencies: Due within this iteration or having an impact on the iteration whether a give or a get dependency.

## Slide 9: Delivery Plan: page 1 of [N]
 | Iteration 19 | Iteration 20 | Iteration 21
 | [04/09] – [04/22] | [04/23] – [05/06] | [05/07] – [05/20]
Velocity | 5 [actual] points | 5 [actual] points | [actual] points
Scope | US98261 - 5 Points US98261 Testing for customer eligibility for products like SDFC(234), AFC(AFC), AFCF(AFF) and AF (New RFISC codes) for SSM | 5 Points 109954 Testing for customer eligibility for products like SDFC(234), AFC(AFC), AFCF(AFF) and AF (New RFISC codes) for Gateside | 109953 SPIKE -Gateside code merge integration US 85870 SPIKE O/D city and class of service of boarding card US106430 SPIKE -Multi segment to provide SDS offer when any segment does not have E - inventory available
Issues | Detailed covered in issue Mgmt. |  | […]
Architecture Decisions | […] | […] | […]
Dependencies | [Due to …] [Due from…] | [Due to …] [Due from…] | [Due to …] [Due from…]
Business Decisions/Impacts | […] | […] | […]
Notes: Since a release plan exists for each release, the number the iterations will be for the release, so X=first iteration number for this release.
As you begin each iteration, verify the previous iterations details are updated to reflect the iteration outcome and then note the new iterations plan. This document replaces your Project Management plan and will serve as a primary communication vehicle for your project. The information on this slide can be copied into the Steering Committee Update Template as your project progresses.
Velocity: Should show values for both planned and actual amounts of work delivered.
Scope: Will show the stories scheduled to be delivered within the iteration. When updating based on actual results, indicate any user stories that were not completed by formatting the story name in italics. These stories should then appear again in the iteration where they will be complete.
Issues: Should reflect those issues that were a significant block for the team during the iteration
Dependencies: Due within this iteration or having an impact on the iteration whether a give or a get dependency.

## Slide 10: Delivery Plan: page 1 of [N]
 | Iteration 22 | Iteration 23 | Iteration 24/25/26/
 | [05/21] – [06/03] | [06/04] – [06/17] | [05/07] – [05/20]
Velocity | [actual] points | [actual] points | 5 [actual] points
Scope | Integration testing and unit testing Automation QA and defect fixes | Integration testing Automation QA and defect fixes | Code Freeze date June 20th Integrated QA ( IQA) 6 weeks period until July 25th Production.
Issues | Detailed covered in issue Mgmt. |  | […]
Architecture Decisions | […] | […] | […]
Dependencies | [Due to …] [Due from…] | [Due to …] [Due from…] | [Due to …] [Due from…]
Business Decisions/Impacts | […] | […] | […]
Notes: Since a release plan exists for each release, the number the iterations will be for the release, so X=first iteration number for this release.
As you begin each iteration, verify the previous iterations details are updated to reflect the iteration outcome and then note the new iterations plan. This document replaces your Project Management plan and will serve as a primary communication vehicle for your project. The information on this slide can be copied into the Steering Committee Update Template as your project progresses.
Velocity: Should show values for both planned and actual amounts of work delivered.
Scope: Will show the stories scheduled to be delivered within the iteration. When updating based on actual results, indicate any user stories that were not completed by formatting the story name in italics. These stories should then appear again in the iteration where they will be complete.
Issues: Should reflect those issues that were a significant block for the team during the iteration
Dependencies: Due within this iteration or having an impact on the iteration whether a give or a get dependency.

## Slide 11: Risks
Risk | Iteration | Related Story | State | Prob | Impact
(CS version 13.0.1. Catalog version 12) CS sending the correct Catalog offers based on the business rules. | 16- 23 | 102305,102316, 106430,98261,100759,106612 | Open | High | High
eTDS performs the fulfillment /payment for SSM requests. | 16- 23 | 108348,106612, 98261 | Open | High | High
Ecloud project go-live dates are critical and its schedule affects SSM launch |  |  | Open | High | High
SSM receives all the needed responses from iTKTs. | 16- 23 | 108348,106612, 98261 | Open | High | High
Code merge issues with Gateside code | Iteration 20 | 106612,102316, 109954 | Open | Medium | Medium

## Slide 12: Dependencies
Gives
Item | To | Iteration | Story | Notes
CS Merch (CS version 13.0.1. Catalog version 12) | Common services | 1 to 28 | US109195, US108348, US106612, US100759, US109205, US100756, US102305, US102316, US85870, US98261, US106430 | [notes]
CS Merch | Catalog | 1 to 28 | US102305,US102316, US106430, US98261, US100759, US106612 | 
iTKTs | eTDS | 1 to 28 | US108348,106612,98261 US109195, US108348, US106612, US100759 | 
App Support | Testing | 1- 28 |  | 

## Slide 13: Issue Management
Issue | Status | Notes
[issue] | [status] | [notes]
756 | OPEN | In a multi-segment any segment offer SDS
?? | OPEN | **Catalog is returning two standby offers for elite passengers
757 | OPEN | offer SDFC or SDS to Mexico
730 | OPEN | Unable to display Alternate Flights if psgr has previously confirmed a flight change
** Pl refer the next slide: |  | 

## Slide 14: Issue : Contd.. Expected results / Actual results
Elite single segment | One SDFC offer with price if not on full fare or bundle 2 and one SDS offer without price depending on the eligibility. Per rule 640: Elite Passengers are eligible for both AS and SDFC offers at the same time and are exempt from AS fees. The response should include SDFC offers (if available) and the Alternate Standby offer for $0. It would not include SDS offers. If both SDFC and AS are offered, the same flights could be in both. | One SDFC offer as expected and two SDS offers with RFISC codes “091” and “AS0” (both without price) A defect will be logged for this. Estimated fix will depend on priority factoring in not just SDFC, but other product releases.
Elite multi segment | One SDFC offer with price if not on full fare or bundle 2 and one SDS offer without price in paired format depending on the eligibility Same comment as above. | One SDFC offer as expected and three SDS offers(for two segment PNR) as below. 1. One with RFISC “091” without price and segments in paired format Defect – should not be in the response. 2. One with RFISC “AS0” without price and flights for first segment only. 3. One with RFISC “AS0” without price and flights for second segment only. I would need to see the PNR to determine if this should be considered 1 or 2 slices/O&D.

## Slide 15: Change Management
Change Request | Status | Notes
[change] | [status] | [notes]
[…] |  | 

## Slide 16: Governance and Escalation
Project Decisions
Product Decisions
Escalation Level | Time | Names | Role
Level One | 1 day | Wajahath Quraishi | Agile Project Lead
Level Two | 2 days | Art Perra | Sr. Project Manager
Level Three – MD or Steering Committee | 4 days | James Barker | Manager
Escalation Level | Time | Names | Role
Level One | 1 day | Jill Curry | Product Owner
Level Two | 2 days | Micheal Bottaro | Manager
Level Three – MD or Steering Committee | 4 Days | Paul Stumbo | MD

## Slide 17: Communication Plan
Item | Objective | Audience | Frequency | Notes
Daily Standup | Update on progress and identify roadblocks | Team | Everyday | 
Backlog Grooming | Prepare user stories for future iteration and ranking | Team | As necessary | 
Iteration Pre Planning | Identify upcoming user stories and review for acceptance criteria and external dependencies | Team | Every Iteration | 
Iteration Planning | Evaluate capacity of team and task breakdown and assignment | Team | Every Iteration | 
Demo | Demo the work completed to product owner | PO, Program team, Tech lead PM | Every Iteration | 
Retrospective | Understand what went well, what went bad and how we can improve | TEAM | Every Iteration | 
[…] |  |  |  | 

## Slide 18: Authors
Collaborative Team
  Jill Curry
  Wajahath Quraishi
  Sheethal Shenoy
  Manjunath
  Chandrasekhar
  Anil

## Slide 19: Review History
Date | Activity | Comments
3/1/2013 | Document created | 

## Slide 20: Revision History
Date | Version | Comments
3/1/2013 | 1.0 |