## Instructions
Instructional Notes for the RACI Diagram
The RACI Matrix is a powerful tool to assist in the identification of roles and assigning of cross-functional responsibilities to a project deliverable or activity.
RACI represents: R - Responsibility, A - Accountable, C - Consulted, and I - Informed
RACI Key:
R=Responsible “The Doer”: Individual responsible for performance and completion of the task
A=Accountable “The Buck Stops Here”: Individual who is answerable for task completion escalation
C=Consulted “In The Loop”: Individual who provides knowledge, information, or expertise before a decision or action is taken
I=Informed “FYI”: Individual who must be informed of the results of a task or process
Simply place an R, A, C, I or any appropriate combination in each of the applicable roles for each activity. Each activity should have one and only one individual Accountable while there may be shared responsibilities depending on the activity.
In Cell 2 B-M - ensure that the named resource is listed for who is playing the role in cell 1 B-M
NOTE: Due to the differences in the RACI for LASH, we have developed a customized version of this to meet their business needs. Only those that are part of CAT/PAT teams and are working Client or Patient services rollouts should use the RACI_Lash template
On the RACI_Lash tab, the items marked in a "peach" color are how the standard RACI differs from the Lash RACI

## RACI Agile
Role | IT Project Sponsor | RM | PM / Scrum Master | Business Product Owner | IT Product Owner | Solution Architect | Solution Analyst | Dev Mgr | Scrum Team / Delivery | Tester | Change Coordinator | Release Engineer | ARB | SRB | Marketing | Project Steering Committee | SD/ST | PAC | CAB
Named Resource | Jeannie Robertson | Dave Meyers | Scicley Christian | Business - Joe DiStefano | IT - Vinjay Gangadharan | Sridhara Madhugiri | Michael Keenan |  |  | Sudhir Reddy |  |  | Sridhara Madhugiri | Sridhara Madhugiri | TBD | Many | Jeannie Robertson | Dave Meyers | Colin Hunt
Note/Comment | [7 empty] | Role not needed | Role not needed | Role not needed? Test Strategy | Role not needed | Role not needed |  |  |  | See PMP | Role not needed | Role not needed | Role not needed
Initiation
Raise Idea / Epic | R/A | R | I | - | - | R | - | [5 empty] | - | -
Prepare Business Case | C | R/A | - | - | - | R | - | [5 empty] | - | -
Prepare High Level Scope Statement | R/A | R |  | R | R | R | - | [5 empty] | - | -
Prepare Rough Order of Magnitude (ROM) estimate | I | C |  | - | R | R/A | R | [5 empty] | C | C
Prepare / Update Portfolio Backlog (including Features) | I | R/A | I | - | - | I | - | [5 empty] | - | -
Prepare / Update Product Backlog (including Features) | - | - | - | R/A | R/A | R | - | [5 empty] | - | -
Prioritize Project | I | R/A | I | R | R | C | R | [5 empty] | - | -
Prepare / Update Solution Proposal | - | I | C | - | R | R/A | R | [5 empty] | - | -
Review & Approve New Technology Standards (ARB) | I | I | I | - | R | R | - | [5 empty] | R/A | -
Review & Approve Solution Architecture (SRB) | I | I | I | - | R | R | - | [5 empty] | - | R/A
Prepares/Update/Approve Project Charter | R/A | C | R | C | R | R | - | [5 empty] | I | I
Prepare High Level Estimates & Costs | I | C | R/A | I | R | R | - |  | C |  |  |  | R | -
Raise Capital / Operating Expenditure Request (CER / OER) | R/A | R | R | - | R | C | - | [5 empty] | C | -
Verify Readiness to go to the next phase (Initiation Stage Gate) | R/A | R | I | I | I | I | [6 empty] | C
Discovery/Requirements & Release Planning
User Story Writing |  |  | I | R/A | R/A | I | R | C | C
Technical Story Writing |  |  | I | C | R | R/A | C | R | R
Release Planning & Sizing Exercise |  |  | C | R | R | I | C | R/A | R
Update Prioritized Product Backlog |  |  | - | R/A | R/A | I | I | - | -
Create Definition of Done |  |  | - | - | - | C | - | R/A | R
Create Test Strategy | C |  | C | - | - | C | C | C | C | R/A | [5 empty] | I
Create Transition Plan |  |  | A | C | C | C | R | R | R
Prepare/Update Release Backlog |  |  | R | R/A | R/A | - | R | R | R
Add Acceptance Criteria for Release |  |  | R | R | R | I | R/A | C | C
Prepare Release Plan |  |  | R/A | C | C | I | C | C | C
Prepare/Update Sprint Backlog |  |  | C | R/A | R/A | - | R | R | R
Add Acceptance Criteria for Sprints |  |  | - | R | R | I | R/A | C | C
Prepare/ Update Evaluation Matrix | R | I | I | R/A | R/A | R | R | R | [7 empty] | I
Update Architecture Vision/Runway |  |  | I | C | C | R/A | C | I | I
Prepare/Update Sprint Plan |  |  | R/A | C | C | - | R | R | R
Project Management Plan (PMLC) | C |  | R/A | C | C | C | C | C | [7 empty] | I
Prepare/ Update ARB Presentation | C | I | I | I | R | R | C | [5 empty] | R/A
Prepare/ Update SRB Presentation | C | I | I | I | R | R | C | [6 empty] | R/A
Verify Readiness to go to the next phase (Req/Release Planning Stage Gate) | R/A | R | I | I | I | I | [6 empty] | C
Sprint Execution and Review
Build Solution |  |  |  | I | I |  | C | R | R/A | I | -
Test Solution |  |  |  | I | I |  | C | R | C | R/A | -
Sprint Demonstration |  |  |  | R | R | I | R | I | R/A | I | -
Create build package and Releases for UAT |  |  |  | I | I |  | C | R | R/A | R | - | R
Update Technical Documentation |  |  |  | I | I | C | C | C | R/A | R | -
Performs UAT |  |  |  | R | R |  | R/A | I | C | R | -
Product Owner signs-off UAT |  |  |  | R/A | R/A |  | R | I | I | I | -
Raise RFC for CAB approval |  |  |  | I | I |  | I | I | I | I | R/A
Sprint Retrospective |  |  | R/A | C | C | C | R | R | R | R | -
Verify Readiness to go to the next phase (Sprint Review Stage Gate) | R/A | R | [10 empty] | C | bar: R/A to C
Transition & Deployment
Prepare Transition Plan and Deployment Instruction |  |  | R/A | C | C |  | R |  | R | C |  | C |  |  |  |  | - |  | -
Prepares Cutover Plan and Rollback Plan |  |  | R/A | C | C |  | R |  | R | C | I | - |  |  |  |  | - |  | -
Prepares / Updates Support Artifacts |  |  | C | I | I |  | R/A |  | R | C | I | - |  |  |  |  | C |  | -
Prepares End-User Instruction |  |  | C | C | C |  | R/A |  | R | - | I | R | [6 empty] | -
Provides Training to Support team |  |  | I | I | I |  | R |  | R/A | - |  | C |  |  |  |  | R |  | -
Provides Training to Users |  |  | I | I | I |  | R/A |  | R | - |  | C |  |  |  |  | R |  | -
Verify Readiness to deploy in Production (Transition & Deploy Stage Gate) | R | C | [9 empty] | R |  |  |  | R/A | C |  | I | bar: R/A to C; R; R to -
Review & Approve RFC for Deployment in Production | R |  | I | C | C |  | C |  | R | I | R | C |  |  |  | I | I |  | R/A
Deploys Release in Production |  |  | I | I | I |  | I |  | R | - | I | R/A |  |  |  | I | C |  | I
Initiate CMDB process as per Transition Plan | [11 empty] | R/A |  |  |  | I | R |  | - | bar: R/A; R; R; -
Verify Deployment in Production |  |  | R | R | R |  | R/A |  | R | C | - | R |  |  |  | - | R |  | -
Provides Hypercare Go-live support |  |  | R | I | I |  | R |  | R/A | R | I | R |  |  |  | I | R |  | -
Hand-over with Support Team | [11 empty] | I |  |  |  | I | R/A |  | I | bar: R/A to C; R; R to -
Project Closure
Conduct Lessons Learned | C | C | R/A | C | C | C | C | C | C | C | - | - | - | - |  | I | - | - | -
Prepare Project Closure Report | I | I | R/A | C | C | C | C | C | C | C | - | - | - | - |  | C | - | - | -
Closure Stage-gate | C | C | R/A | C | C | C | C | C | C | C | C | C |  |  |  | C | C

## RACI Agile_LASH (hidden)
Role | IT Project Sponsor | RM | PM | Product Owner | Solution Architect | Solution Analyst | Scrum Master / Dev Mgr | Scrum Team / Delivery | Tester | Change Coordinator | Release Engineer | ARB | SRB | Project Steering Committee | SD/ST | PAC | CAB | LASH Specific guidance/comments
Named Resource
Initiation | Program Mgr | Fred Ricer |  | BPO |  | See Comment
Raise Idea / Epic | - | - | I | R/A |  | - | [5 empty] | - | - |  |  |  |  | In PTR/Clarity-ADR
Prepare Business Case | C | R/A | - | - | R | - | [5 empty] | - | - |  |  |  |  | Applicable for a net new solution (i.e. new product, new functionality); which typically falls into Prod dev projects
Prepare High Level Scope Statement | C | C | C | R/A | C | - | [5 empty] | - | - |  |  |  |  | In PTR/Clarity-ADR
Prepare Rough Order of Magnitude (ROM) estimate | R | C | I | - | R/A | R | [5 empty] | C | C |  |  |  |  | If Solution Architect involved; typically meaning a Business Case was generated.
Prepare / Update Portfolio Backlog (N/A) | I | R/A | I | - | I | - | [5 empty] | - | - |  |  |  |  | This is not applicable to Lash present day.
Prepare / Update Product Backlog | - | I | I | R/A | C | - | [5 empty] | - | -
Prioritize Project | I | R/A | I | - | C | - | [5 empty] | - | - |  |  |  |  | Obtain priority If Business Case was generated.
Prepare / Update Solution Proposal | - | I | C | - | R/A | R | [5 empty] | - | - |  |  |  |  | For net new feature functionality; Development can help provide guidance if needed.
Review & Approve New Technology Standards (ARB) | I | I | I | - | R | - | [5 empty] | R/A | -
Review & Approve Solution Architecture (SRB) | I | I | I | - | R | - | [5 empty] | - | R/A
Prepares/Update/Approve Project Charter | R/A | C | R | C | R | - | [5 empty] | I | I |  |  |  |  | Project Manager responsible for creating Project Charter working with Program Manager. Applicable if 2 or more workstreams (i.e. configuration, data migration, etc.)
Prepare High Level Estimates & Costs | I | C | R/A | I | R | - |  | C |  |  |  | R | - |  |  |  |  | Level 1 Estimate provided in PTR or Clarity-ADR
Raise Capital / Operating Expenditure Request (CER / OER) | R/A | R | R | - | C | - | [5 empty] | C | - |  |  |  |  | Validate with BPO to move forward based on estimates.
Verify Readiness to go to the next phase (Initiation Stage Gate) | R/A | R | I | I | I | [6 empty] | C
Requirements & Release Planning | [5 empty] | Business Analyst | [11 empty] | Feature Level
User Story Writing |  |  | I | R/A | I | R | C | C | [9 empty] | BPO creates feature story; In Sprint/Execution Phase: BA will breakdown features into right size user stories
Technical Story Writing |  |  | I | C | R/A | C | R | R
Release Planning & Sizing Exercise |  |  | C | R | I | C | R/A | R
Update Prioritized Product Backlog |  |  | - | R/A | I | I | - | -
Create Definition of Done |  |  | - | - | C | - | R/A | R
Create Test Strategy | C |  | C | - | C | C | C | C | R/A |  |  |  |  | I
Create Transition Plan |  |  | A | C | C | R | R | R | [9 empty] | Living document; Includes Deployment Instructions
Prepare/Update Release Backlog |  |  | R | R/A | - | R | R | R
Add Acceptance Criteria for Release |  |  | R | R | I | R/A | C | C
Prepare Release Plan |  |  | R | R | I | C | R/A | C
Prepare/Update Sprint Backlog |  |  | C | R/A | - | R | R | R | [9 empty] | R's based on ensuring the team speaks up and actively updates/add stories as they need
Add Acceptance Criteria for Sprints |  |  | - | R | I | R/A | C | C | [9 empty] | Ensure Definition of Done is met
Update Architecture Vision/Runway |  |  | I | C | R/A | C | I | I
Prepare/Update Sprint Plan |  |  | R | C | - | R | R/A | R
Project Management Plan (PMLC) | C |  | R/A | C | C | C | C | [6 empty] | I |  |  |  | PM responsible for creating per client and reviewed quarterly or as needed to ensure up to date.
Verify Readiness to go to the next phase (Req/Release Planning Stage Gate) | R/A | R | I | I | I | [6 empty] | C
Sprint Execution and Review | [17 empty] | Story Level= Decomposition
Build Solution |  |  |  | I |  | C | R | R/A | I | -
Test Solution |  |  |  | I |  | C | R | C | R/A | -
Sprint Demonstration |  |  |  | R | I | R | I | R/A | I | -
Create build package and Releases for UAT |  |  |  | I |  | C | R | R/A | R | - | R
Update Technical Documentation |  |  |  | I | C | C | C | R/A | R | -
Performs UAT |  |  |  | R |  | R/A | I | C | R | - | [7 empty] | Assume the BA is an extension of the BPO; working toward new process.
Product Owner signs-off UAT |  |  |  | R/A |  | R | I | I | I | - | [7 empty] | Will be a TFS story and approved by BPO.
Raise RFC for CAB approval |  |  |  | I |  | I | I | I | I | R/A | [7 empty] | May be PM acting in Change Coordinator role
Sprint Retrospective |  |  |  | C | C | R | R/A | R | R | -
Verify Readiness to go to the next phase (Sprint Review Stage Gate) | R/A | R | I | I | I | [6 empty] | C
Transition & Deployment
Prepare Transition Plan and Deployment Instruction |  |  | R/A | C |  | R |  | R | C |  | C |  |  |  | - |  | -
Prepares Cutover Plan and Rollback Plan |  |  | R/A | C |  | R |  | R | - | I | - |  |  |  | - |  | -
Prepares / Updates Support Artifacts |  |  | C | I |  | R/A |  | R | C | I | - |  |  |  | C |  | -
Prepares End-User Instruction |  |  | C | C |  | R/A |  | R | - | I | R |  |  |  | I |  | - | Update SOPs and tailor for clients if applicable.
Provides Training to Support team |  |  | I | I |  | R |  | R/A | - |  | C |  |  |  | R |  | - | If applicable
Provides Training to Users |  |  | I | I |  | R/A |  | R | - |  | C |  |  |  | R |  | - | If applicable
Verify Readiness to deploy in Production (Transition & Deploy Stage Gate) |  |  | R | R |  | R |  | R | R | I | R |  |  | R/A | C |  | I | Stage Gate step; ensuring risks are closed/mitigated for moving forward with deployment
Review & Approve RFC for Deployment in Production | I |  | I | C |  | C |  | R | I | R | C |  |  | I | I |  | R/A
Deploys Release in Production |  |  | I | I |  | I |  | R | - | I | R/A |  |  | I | C |  | I
Initiate CMDB process as per Transition Plan |  |  | R |  |  | - |  | C | - | R | R/A |  |  | I | R |  | -
Verify Deployment in Production |  |  | R | R/A |  | R |  | R | C | - | R |  |  | - | R |  | - | Solution Analyst is 'I';Delivery is 'R'; BPO is 'R/A'
Provides Hypercare Go-live support |  |  | R | I |  | R |  | R/A | R | I | R |  |  | I | R |  | -
Hand-over with Support Team |  |  | R | I |  | R |  | R | I | I | I |  |  | I | R/A |  | I
Project Closure
Conduct Lessons Learned (Project Level) | C | C | R/A | C | C | C | C | C | C | - | - | - | - | I | - | - | -
Prepare Project Closure Report | I | I | R/A | C | C | C | C | C | C | - | - | - | - | C | - | - | -
Closure Stage-gate | C | C | R/A | C | C | C | C | C | C | C | C |  |  | C | C

## Role Descriptions
Role | Responsibility
IT Project Sponsor | Responsible for overall accountability within IT for the project
Relationship Manager (RM) | Responsible for the intake of business requested projects, changes or requests. Works with the business to establish the priority for agreed to solutions.
Solution Analyst | Responsible for gathering and documenting the functional and non-function requirements - including business, infrastructure and security. Documents the Functional Design. Works with the end user to develop UAT Test Cases and owns UAT Testing Responsible for pre-qualification of standard change , Ensure relevant documentations / SOPs available for standard change, Verify readiness of solution for deployment in production in case of Standard Change Provide feedback on daily work for Agile Lifecycle
Project Manager | Responsible for Project Planning, Monitoring & Controlling, and Project Change management Release Planning, Sprint Planning / Re-planning, Hosts Sprint Retrospection with team and prepares retrospection report for Agile Lifecycle
Project Steering Committee | Project governing body with responsibility of approval of project size/effort, schedule, Stage Gates to ensuring readiness to move into UAT and production.
Delivery | Responsible for preparing Technical Design Document ,for building the solution -this includes application development, infrastructure, configuration, and security. Owns Unit Testing. Responsible for packaging solution for Repeatable Deployment. Responsible for Analyzing and fixing bug in case of Bug Fixing Responsible for build & Test Solution for Standard Change Perform daily Development, Provide Product Walkthroughs, Package the Solution ,Share Sprint Review Report for Agile Lifecycle
Tester | Responsible Preparing Test Strategy, Plans and Cases for solution testing - Integration, functional, system, performance, load, security/penetration, automated, validation, HA/failover and hardware testing. Responsible for bug-fix solution testing
Release Engineer | Deploy Build in all environments
Change Coordinator | Role responsible for creating Request for Change (RFC) and tracking the RFC status for Production Change
Enterprise Architect (EA) | Responsible for working with Solution Architect(s) to consider leverage of Current Technology Assets or opportunities for new and different technology assets
Solution Architect (SA) | Various technology leads within the organization including someone from Solution Architecture, Security, Infrastructure teams, can play this role. You may also have multiple people playing this role however, one should be designated as pulling together the end to end solution. Estimates Rough Order of Magnitude (ROM) for Idea with the help of Solution Analyst Responsible for preparing the Solution Proposal with the help of Solution Analyst. Raising ARB request with the help of Solution Analyst for review of Architecture by ARB if new technology is being added to the enterprise. Ensuring the appropriate signatories approve the TDD in preparation for the Design stage gate.Add Technical Stories and Create / Update Architecture Vision/Runway in case of Agile Lifecycle
Agile - Product Owner | Decompose Epics to Stories and Prioritize ,Maintain & Prioritize product backlog, Prepare/Update Sprint Backlog, Provide feedback on daily work , Approves UAT
Agile - Scrum Master | Release Planning & Sizing ,Creation of Definition of Done , Creation of Test Strategy, Transition Plan
IT Finance Liaison (SPOC) | These aligned Financial Resources are engaged during Annual Portfolio Planning and for any new projects or programs that will be added to the portfolio after annual planning. They provide Financial Approval for all IDEA’s prior to going to the PAC.
Portfolio Coordinator | This role is responsible to manage their respective Portfolio(s) for the following: Acquire financial approval from the IT Finance Liaison, understanding of what projects are ‘above the water line’ for the fiscal year, negotiate project scope changes with the business and IT, and approve new projects to be added to their Portfolio.
Financial Controller | This can be either the Business or IT Financial controller who manages the budget for that initiative. They are responsible to make any necessary budget adjustments for changes in scope and annual planning.
BOARDS
Role | Responsibility
Architecture Review Board (ARB) | EITS governing body with approval responsibility of any new Technologies being added to the Enterprise.
Solution Review Board (SRB) | EITS governing body responsible for reviewing and approving solution design (Technical Design Document and Functional Design Document) before build phase starts.
Change Advisory Board (CAB) | EITS governing body with review & approval responsibility of Request for Change (RFC). Request for Change is the change for the deployment in production
Project Change Control Board (PCCB) | EITS governing body with review & approval responsibility of project change request.