## Action Log
Date Raised | Summary | Comments | Owner | Due Date | Priority | Status
2018-09-26 | Recurring schedule of Backlog Grooming meetings | Tracey to propose cadence of Backlog Grooming meetings through Discovery period | Tracey |  | High
2018-09-26 | Interim Solution for WAM | Ian to complete write up on Auth0 | Ian |  | High
2018-09-26 | Provide documentation on QA Services | Tracey / Mike to meet and prepare document ahead of Monday OCT 1 meeting | Mike S |  | High
2018-09-26 | Documention on Key Areas of Project Methodology | Approach to estimating, Definition of Done, key aspects of Agile methodology we will be following | Tracey |  | Low
2018-09-26 | Raid Activity | Sort through post its, stand Risk Log | Tracey |  | High
2018-09-26 | Drivers Activity | Sort through post its and summarize in document | Tracey |  | Med
2018-09-26 | Access to Back End Systems | Vinay to ensure GH team has access through internal firewall to communicate with, for example, Mulesoft. VPN on VM? Can we whitelist? | Vinay |  | High
2018-09-26 | Documentation on Mulesoft APIs | High level documentation for each API and example of a JSON response for each. | Sahana /Venu |  | High
2018-09-26 | Backlog Export from TFS | Teams to export CSV or XLS file from TFS until we have access to JIRA. | Mike K / Joe |  | Med | Complete
2018-09-26 | Access to JIRA | Ensure all GH team members have access to the WC JIRA instance | Vinay |  | High | In Progress
2018-09-26 | Design - Competitor Analysis | Joe to share with GeekHive along with likes/dislikes and aspirations | Joe |  | Med
2018-09-26 | Hosting - Cloud vs On Prem | WC team to make a decision and reach out to GH with for consultation | Sri |  | Med
2018-09-26 | Design - Review DSG | Tracey / Brandon to review current Design Style guide and assess missing pieces needed for CP20 design | Tracey / Brandon |  | Med
2018-09-26 | Interviews of Sitecore Developers | Let us know when you'll be ready and how many canditates are planned. Need to determine the level of GH time allocation to this effort. | Venu/Sahana |  | Low
2018-09-26 | WAM Replacement | Tracey to reach out to scicley and get more info about the long term plan for this before we provide Auth0 reco. | Scicley |  | Med
2018-09-26 | Schedule meeting for OCT 1 about QA | Tracey will reach out and propose times to WC team | Tracey |  | High
2018-09-26 | Browser Support | GH to provide list of browsers / versions / OS are in scope for this project, WC team to confirm based on current site analytics. | Tracey |  | Low
2018-09-26 | Technical Design | Server Architecture and system communications Technical Documentation Requirements Schedule a meeting on what should be documented | Tracey |  | High
2018-09-26 | Server Diagram for ABC Program set up | Find and Share documentation with WC team | John R |  | Low
2018-09-26 | Schedule Daily Standups | Confirm time of day and when to start | Tracey |  | Low
2018-09-26 | Documentation on User Management | Vinay mentioned documentation around a "user roles Matrix". Can we get a copy of this? Is this documented within the User Stories? Relationship between Companies, Users, and Projects. | Vinay |  | Med
2018-09-26 | Analytics | Ensure user stories for Analytics are documented to show specific metrics that we need to track | Mike K |  | Low
2018-09-26 | Source Control Repository | TFS? Confirm tool we're using / We are using JIRA | Waj |  | High
2018-09-26 | Build and Release Management Tool | TFS? Confirm tool we're using | Sahana/ Sudhir |  | High
2018-09-24 | SiteCore development Approach: ABC choice ? | Approach can be a mix of Tradition, Progressive Decoupling and Headless. Or a combination of the three | Sri |  | Med
2018-09-24 | Front end libraries or framework | If ABC has any preferences for/against Front end libraries/framework | Sri | None identified | Med

## Risk Log
Date Raised | Risk Detail | Mitigation Plan | Probability | Severity | Owner
2018-09-26 | MVP Priorities | Prioritze jira stories within MVP - Must, Should, Won't, etc
2018-09-26 | Lack of clear documentation / access to APIs
2018-09-26 | Right to Left Languages | Identify RtL languages and consider any design/dev challenges
2018-09-27 | Dependency between both Workstream | Use the dependency matrix between work steams and improved collabration and dedicated lead resource for CP

## Decision Log
Date Raised | Summary | Decision Detail
2018-09-24 | Version Sitecode | We will use Sitecore version 9.
2018-09-24 | Tool Repositiry | We will be using the Jira on the ABC side.
2018-09-24 | Testing | Who does what testing between GH and ABC . Discussion to be scheduled -> Scicley
2018-09-24 | Environment | GH Application development will connect with ABC QA environment interface while develop their code.
2018-09-24 | Architecture: | CMS Sitecore instance: We already have one instance for Marketing and we will have a new one for MVP.

## Roles and Responsibilities
Name | Email | Role | Scope /Priorities (MVP) | Facilitite GH needs / | Front end Development | Project Management reporting / Tracking (Front end) | Backend Development | Project Management reporting / tracking (Backend) | Quality /Testing (Work in progress)
Scicley Christian | scicley.christian@absg.com | Program Manager | S,I,C | S,C,I | S,I | S,C,I | S,I | S,C,I | S,I
Sridhara Madhugiri (Sri) | smadhugiri@amerisourcebergen.com | Solutions Architect | S,I,C | S,I | S,I,C | S,I | R,C,S | S,I | S,I
Sudhir Reddy | sudhir.reddy@absg.com | QA Manager | S,I,C | S,I | S,I | S,I | S,I | S,I | R,S,I,C
Sahana Reddy | Sahana.Reddy@absg.com | AppDev Manager | S,I,C | S,I | S,I,C | S,I | A,R,C,S | S,I | S,I,C
Govind Bundawala | Govind.Bundawala@absg.com | Appliation Architect (Backend) | S,I,C | S,I | S,I | S,I | R,C,S | S,I | S,I,C
Joe distefano | distefano@worldcourier.com | Product Manager | R,C,S | S,C,I | S,I,C | S,I,C | S,I,C | S,C,I | S,I,C
Vinay Gangadharan | VGangadharan@amerisourcebergen.com | Product Owner | A,R,C,S | S,C,I | S,I,C | S,I,C | S,I,C | S,C,I | S,I,C
Keenan, Michael | MKeenan@amerisourcebergen.com | Business Analyst (Front end - switch to backend) | S,I,C | S,I | S,I,C | S,I | S,I,C | S,I | S,I,C
Venkat Bole | Venkat.Bole@LashGroup.Com | Validation Tester | S,I,C | S,I | S,I | S,I | S,I | S,I | S,I,C
Elren Huff | Elren.Huff@absg.com | Project Manager (Backend ABC) | S,I,C | S,I | S,I | S,I,C | R,C,S | A,R,C,S | S,I,C
Wajahath Quraishi (Waj) | Wajahath.quraishi@absg.com | Scrum Master (Front end ABC) | S,I,C | A,R,C,S | S,I | R,C,S | S,I | S,C,I | S,I,
GH
Tracey |  | Scrum Master (GH) | I,C | R,S,I,C | R,C,S | A,R,C,S | C,I | S,C,I | S,I,
Ian Poley |  | Tech Lead (GH) | I,C | S,I,C | A,R,C,S | S.I | C,I | S,I | S,I,C
Mike |  | QA Manager (GH) | [6 empty] | R,S,I,C
R - Responsible - who is responsible for carrying out the entrusted task
A - Accountable (also Approver) - who is responsible for the whole task and who is responsible for what has been done?
S - Support - who provides support during the implementation of the activity / process / service
C - Consulted - who can provide valuable advice or consultation for the task
I - Informed - who should be informed about the task progress or the decisions in the task

## RiskLog_Mitigated (hidden)
Risk Log - Mitigated
Date Raised | Risk Detail | Mitigation Plan | Probability | Severity | Owner | Status

## ActionLog_Complete (hidden)
Action Log - Complete
Date Raised | Summary | Comments | Owner | Due Date | Priority | Status