## Key
Key | Category | Description
R | Responsible | Performs the activity or does the work
A | Accountable | Accountable for the activity
C | Consulted | Provides feedback and contributes to the activity
I | Informed | Needs to know about any decisions or actions made
Key | Person or Group | Role
TB | Tim Butler | GeekHive Account Manager
JR | John Rappel | GeekHive .NET Practice Lead
TR | Tracey Robinson | GeekHive Project Producer
BM | Brandon Mosley | GeekHive Design
IP | Ian Poley | GeekHive Tech Lead
GH DEV | GeekHive Dev Team | Sitecore Backend Developer, Front End Developer, UX Developer
GH QA | GeekHive QA Team | GH QA Analyst

## Deliverable Responsibilities
|  | GeekHive | [6 empty] | World Courier / ABC
Deliverable | Responsibility | TB | JR | TR | IP | BM | GH DEV | GH QA |  | Notes
Project Discovery
| Production Environment Architecture | I | C | I | RA | - | - | -
| Development Approach | I | C | I | RA | - | I | C
| Quality Assurance Approach | I | I | A | C | - | - | R
| Sitemap | I | I | CI | C | RA | I | -
| Wireframes | I | I | CI | C | RA | C | I
| Mockups | I | I | CI | C | RA | C | I
| High Level User Story Estimates | - | - | A | R | - | - | -
Implementation / Post Launch Support
| Daily Standups | I | I | RA | R | - | R | C
| Backlog Grooming | I | I | A | RA | I | C | I
| Sprint Planning | I | I | RA | R | I | R | C
| Demos | I | I | A | R | - | R | C
| Retrospectives | I | I | RA | R | - | R | C
| User Story Estimates | - | - | A | RA | - | R | R
| Development | I | C | I | RA | - | R | I
| Code Revews | - | I | I | RA | - | R | I
Quality Assurance
| Manual Functional Testing | I | I | I | CI | - | CI | RA
| Integration Testing | I | I | CI | CI | - | CI | CI
| Validation Testing | I | I | CI | CI | - | CI | CI
| Performance Testing | I | I | CI | CI | - | CI | CI
| End to End Testing | I | I | CI | CI | - | CI | CI
| Security Testing (Penetraion Testing) | I | I | CI | CI | - | CI | CI
| User Acceptance Testing | I | I | CI | CI | - | CI | CI
| Demos: Automation Testing |  | Approach to Automation requires Discussion between Tim / Joe / Jay / Venu
Reporting
| Weekly Status Reporting | I | I | RA | CI | CI | CI | CI
| Project Plan | I | I | RA | CI | CI | CI | CI
| Project Log - Actions, Risks, Decisions | I | I | RA | CI | CI | CI | CI
| Meeting Scheduling / Coordination | C | C | RA | CI | CI | CI | CI
| Documentation | C | C | RA | R | R | R | R |  | Assignment will vary by Document Type