## Sheet1
02/27 - 3/12 | 3/13-3/19 | 3/20-4/2 | 4/3-4/17 | 4/18 -5/1 | 5/2-5/15 | 5/16-5/28 | 5/29 -6/11 | 6/12 -6/25 | 6/26-7/09 | 7/10-7/23 | 7/24-8/6 | 8/7 - 8/20 | 8/21 -9/3 | 9/4 -9/8 | 2019-09-09 | 9/10 - 9/30
Iter 1 | Iter 2 | Iter 3 | Iter 4 | Iter 5 | Iter 6 | Iter 7 | Iter 8 | Iter 9 | Iter 10 | Iter 11 | Iter 12 | Iteration 13 | Iteration 14 | Prod Deployment | Go Live
[12 empty] | Bug Fixes & Support | Bug Fixes & Support |  |  | Hypercare Support
Hypercare Support
Complete development /Build and unit testing
E2E Testing(Stage)
Performance Scripting & Testing(Stage)
Validation(Stage)
DAST Security (QA)
UAT (Stage)
SAST Security Testing (QA)

## Sheet2 (hidden)
01/30 - 2/5 | 2/13-2/19 | 2/20-2/26 | 2/27-3/5 | 3/6-3/13 | 3/14-3/20 | 3/21-3/27 | 3/27-3/31 | 2019-04-01 | 4/1-4/26
Iteration 7 | Iteration 8 |  | Iteration 9 |  | Iteration 10 |  | Prod Deployment | Go Live
Frontend UStories | Frontend UStories |  | Geekhive Support |  | Geekhive Support |  |  |  | Hypercare Support
Backend Ustories | Backend Bug Fixes |  | Backend Bug Fixes & Support |  | Backend Bug Fixes & Support |  |  |  | Hypercare Support
Assumptions/Risks
MDM data loads will be available in Stage by the time E2E testing starts-Data migration from current ODS to new ODS will be in place.WAM data migration should be complete
UAT and Validation will go in parallel-so any UAT defects need to account for any impact to Validation-this might impact program go live date
Security and Performance teams need to coordinate for execution
Standard timeline for validated platforms is usually 2 weeks of execution time.
Complete frontend-backend integration testing
E2E Testing(Stage)
Performance Scripting & Testing(Stage)
Validation(Stage)
DAST Security (QA)
UAT (Stage)
SAST Security Testing (QA)