## Backlog
ID | Work Item Type | Title 1 | Title 2 | Title 3 | State | Tags | Salesforce
90078 | Epic | New Trial Setup |  |  | New | Core Build 1
90097 | Feature |  | Provide a Homepage/Dashboard |  | New | XXL | 160
90219 | User Story |  |  | Ability to land on the application Home Page | New
92979 | User Story |  |  | Create a Clinical Trial Study Maintenance Dashboard | New
94535 | User Story |  |  | Create Protocol Maintenance Dashboard | New
93220 | User Story |  |  | Create an Item Maintenance Dashboard | New
93277 | User Story |  |  | Create a Consignee Maintenance Dashboard | New
93406 | User Story |  |  | Create a Shipper Maintenance Dashboard | New
93715 | User Story |  |  | Create Customer Service Dashboard/Homepage | New
90098 | Feature |  | Create and Add a new Study/Project |  | New | eMDM; XL | 120
90220 | User Story |  |  | Create a new Study/Project with required information | New
92980 | User Story |  |  | Add contact details at Study/Project level | New
92981 | User Story |  |  | Add Notes at Study/Project level | New
97442 | User Story |  |  | Upload and attached study level documents | New
90104 | Feature |  | Create and Add a Protocol within a Study/Project |  | New | eMDM; XL | 120
90279 | User Story |  |  | Add a protocol with all the relevant details | New
92983 | User Story |  |  | Ability to copy details from an existing protocol to a new protocol | New
92984 | User Story |  |  | Add Contacts detail at Protocol Level | New
93196 | User Story |  |  | Add Dangerous Goods (DG) contact details at Protocol Level | New
92985 | User Story |  |  | Add Notes at Protocol Level | New
93003 | User Story |  |  | Ability to place a HOLD at Protocol level | New
97443 | User Story |  |  | Select Specialty Services for a protocol | New
97444 | User Story |  |  | Upload and attached Protocol Level Documents | New
90099 | Feature |  | Add an Item within a Protocol |  | New | XL; TMS; WORLD-STAR | 120
90294 | User Story |  |  | Add an Item to a Protocol with all the required information | New
93222 | User Story |  |  | Select required Item from an Item Table | New
93223 | User Story |  |  | Select required class from classification table | New
93225 | User Story |  |  | Select required Temp_Opt from Temperature Option Table | New
92997 | User Story |  |  | Select required documents from the Documents table | New
92998 | User Story |  |  | Select required packaging from Packaging Table | New
92999 | User Story |  |  | Select required Refrigerant option from Refrigerant Table | New
90306 | User Story |  |  | View an Item overview within a Protocol | New
93000 | User Story |  |  | Add notes to an Item | New
90100 | Feature |  | Add a Consignee to a Protocol |  | New | eMDM; XL | 120 | Size | Hours
90310 | User Story |  |  | Create a new Consignee with required information | New
90350 | User Story |  |  | Assign driveaway APC based on the address entered at Consignee Level | New
90334 | User Story |  |  | Add Consignee Primary and Secondary Contacts details | New
93011 | User Story |  |  | Add Consignee DG Emergency Contact details | New
93014 | User Story |  |  | Add notes at Consignee level | New
90348 | User Story |  |  | Ability to bulk upload Consignee Site addresses | New
97496 | User Story |  |  | Attached and Upload required documents for a Consignee | New
90101 | Feature |  | Add a Shipper to a Protocol |  | New | eMDM; XL | 120 | S | 40
90308 | User Story |  |  | Create new Shipper with required information | New |  |  |  | 60
93429 | User Story |  |  | Assign driveaway APC based on the address entered at Shipper Level | New |  |  |  | 80
93017 | User Story |  |  | Add Shipper Investigator details | New |  |  |  | 120
93018 | User Story |  |  | Add Shipper Contact details | New |  |  |  | 160
97502 | User Story |  |  | Add Shipper DG contact detail | New |  |  |  | 200
93020 | User Story |  |  | Display a list of all the shipper contacts within a Protocol | New
93019 | User Story |  |  | Add notes at Shipper level | New
90343 | User Story |  |  | Enter Shipping related instruction for Shipper | New
93081 | User Story |  |  | Ability to bulk upload Shipper Site addressess | New
93716 | User Story |  |  | Add Shipper Notification Checklist | New
93718 | User Story |  |  | Ability to create and print Site instruction | New
93719 | User Story |  |  | Standardize a SITE Instruction for global users | New
97503 | User Story |  |  | Attached and upload required documents at shipper level | New
97531 | User Story |  |  | Enter Shipping Instruction at Shipper Level | New
90103 | Feature |  | Link Item-Consignee pairs to Shippers |  | New | XL | 120 | M | 60
90352 | User Story |  |  | Link authorized Items (Commodity+Temp) to applicable Consignees | New
90353 | User Story |  |  | Link Item-Consignee pairs to applicable Shippers | New
90357 | User Story |  |  | Manually bulk link and Unlink Items (Commodity+Temp) to the applicable Consignees and Shippers | New
90354 | User Story |  |  | Have the system assign a default Service Code to each Shipper-Item-Consignee combination | New
90355 | User Story |  |  | Assign one or more Authorized Routes to Shipper-Item-Consignee combinations | New
93087 | User Story |  |  | Add note field for user to enter routing restriction | New
93601 | User Story |  |  | ADD LCT/LPT/RTG details | New
90077 | Epic | Trial and Study Management |  |  | New | Core Build 1
90162 | Feature |  | Ability to make changes at studies/protocol level |  | New | XXL | 160 | L | 80
97632 | User Story |  |  | Display a pop-up message if duplicate found | New
90362 | User Story |  |  | Ability to make changes to study level details including other WC offices | New
92990 | User Story |  |  | Ability to approve a Study/Project | New
90221 | User Story |  |  | Drive the status of a Study/Project based on the effective date | New
93082 | User Story |  |  | Ability to make changes at Protocol Level details including other WC offices | New
90283 | User Story |  |  | Drive the status of a Protocol based on the effective date | New
93091 | User Story |  |  | Ability to print SITE instruction with all Consignees | New
90300 | User Story |  |  | Ability to Edit fields related to an Item | New
90301 | User Story |  |  | Ability to Delete an Item from a Protocol | New
90299 | User Story |  |  | Remove packaging or refrigerant from an Item | New | Need Bus Input
90297 | User Story |  |  | Drive the status for the Packaging or Refrigerant of an Item based on the effective date | New | Need Bus Input
90341 | User Story |  |  | Ability to edit fields related to the Shipper/Consignee | New
90338 | User Story |  |  | Inactivate/Re-Activate/Remove a Shipper/Consignee from a study | New | Need Bus Input
90339 | User Story |  |  | Inactivate/Re-activate/Remove Shipper/Consignee Contacts from a study | New | Need Bus Input
93118 | User Story |  |  | Add/update/remove Notes at Study/Protocol/Item/Shipper/Consignee level | New | Need Bus Input
93307 | User Story |  |  | Ability to add an existing Consignee to a Protocol | New
93308 | User Story |  |  | Ability to add an existing Shipper to a Protocol | New
90346 | User Story |  |  | Create/Remove/Update "master" instructions at different inherited levels | New
90163 | Feature |  | Manage HWBs for a study/protocol |  | New | L | 80 | XL | 120
90364 | User Story |  |  | Manage and track HWBs | New
90382 | User Story |  |  | Generate and Print Pre-printed HWBs for each Site | New
96843 | User Story |  |  | Create an unique HWB number per job | New
90167 | Feature |  | Maintain Site Pack document templates |  | New | L | 80 | XXL | 160
90370 | User Story |  |  | Upload and maintain Site Pack document templates | New
90371 | User Story |  |  | Tailor a Site Pack Template to be Study Specific | New
90372 | User Story |  |  | Save and Maintain the Tailored Study Templates | New |  |  |  | 160
90374 | User Story |  |  | Open, Tweak, and Print a Tailored Study Template for a Site | New
90375 | User Story |  |  | Send Site packs by Mail/Email | New
90376 | User Story |  |  | Record and Manage information related to the progress of sending out Site Packs to Sites | New
90106 | Feature |  | Send alert/notification to impacted users only |  | New | Notification Engine; XXL | 160 | XXXL | 200
93086 | User Story |  |  | Ability to manage Opt in/Opt out options for email notification | New
90379 | User Story |  |  | Send emails out to Contacts (Single or bulk) for a study | New
90367 | User Story |  |  | Record and Maintain all the communication between customer and CTL | New
90360 | User Story |  |  | Ability to send notification between users within the system (Single and/or groups) | New
90347 | User Story |  |  | Send automated change notifications when changes are made to an Instruction | New
90369 | User Story |  |  | Record and maintain all the customer complaints for a study | New
90340 | User Story |  |  | Send automated change notifications when changes are made to a Shipper/Consignee level | New
90359 | User Story |  |  | Send automated change notifications when changes are made to a Study/Project/Protocol/Item level | New
90358 | User Story |  |  | Configure shipment notifications for a Study | New
90384 | User Story |  |  | Send an Alert when new site address added to a study by CSR during shipment booking | New
93093 | User Story |  |  | Ability to send 'on Demand' notification to all the impacted SITE offices. | New |  |  |  | 200
90387 | User Story |  |  | Send Alert to impacted CSR user when making changes to a shipment | New
90388 | User Story |  |  | Send Alert to Impacted CTL users when CSR make changes to a Shipment information | New
90081 | Epic | Shipment Booking and Consolidation |  |  | New | Core Build 1
90174 | Feature |  | Create and submit a shipment for a study |  | New | OOE; TMS; WORLD-STAR; XXL | 160
90385 | User Story |  |  | Create a Booking form for Shipment | New
90383 | User Story |  |  | Add new SITE to a study during Shipment Booking | New
93097 | User Story |  |  | Ability to create parent/child job format | New
93088 | User Story |  |  | Add a routing revision pop-up alert for user | New
90386 | User Story |  |  | Record and Maintain all the changes made by CSR | New
96844 | User Story |  |  | Ability to select packaging from pre-approved List | New
90175 | Feature |  | Shipment consolidation rules for a project |  | New | M | 60
90390 | User Story |  |  | Define shipment consolidation rules sets for projects/Segments (Domestic vs International) | New
90391 | User Story |  |  | Suppress some regularly transmitted fields at any level | New
90091 | Epic | Direct to patient services |  |  | New | Core Build 1
90749 | Feature |  | Direct to Patient (DTP) |  | New | XXL + M | 220
90787 | User Story |  |  | Set DTP service indicator on Bio-STAR | New
90788 | User Story |  |  | Add/Delete DTP service code on Bio-STAR | New
90789 | User Story |  |  | Add/Delete DTP service code on TMS Shipment Screen | New
90791 | User Story |  |  | Transmit DTP fields to Bio-Star integration | New
96839 | User Story |  |  | Flag an item with limited Life Span | New
96842 | User Story |  |  | Special Document handling for DTP services only | New
90080 | Epic | Cell and Gene Therapy services |  |  | New | Core Build 1
90750 | Feature |  | Cell & Gene Therapy |  | New | eMDM; TMS; XXXL + L | 280
90792 | User Story |  |  | Set CGT service indicator on Bio-STAR | New
90793 | User Story |  |  | Add/Delete CGT service code to Bio-STAR | New
90796 | User Story |  |  | Add/Delete CGT service code to TMS Shipment Screen | New
90798 | User Story |  |  | Transmit CGT fields to Bio-Star integration | New
93603 | User Story |  |  | CGT Portal for Client | New
93604 | User Story |  |  | CGT Dashboard/Homepage | New
93605 | User Story |  |  | Tracking CGT shipment | New
97972 | User Story |  |  | Ability to encrypte Confidential Patient Data | New | NFR
90082 | Epic | BioSphere Services |  |  | New | Core Build 1
90751 | Feature |  | BioSphere |  | New | Integrator; XXXL + M | 260
90768 | User Story |  |  | Set BioSphere Service Indicator on Bio-STAR | New
90772 | User Story |  |  | Add/Delete BioSphere code on Bio-STAR | New
90771 | User Story |  |  | Add/view/Update/Delete Bio-Sphere code on TMS Shipment Screen | New
90786 | User Story |  |  | Transmit BioSphere Field to Bio-Star Integration | New
97865 | User Story |  |  | Display a list of third party integrator for BioSphere | New
97866 | User Story |  |  | Provide an URL link for third party integrator with BioSphere service | New
90083 | Epic | Search and Results |  |  | New | Core Build 1
90178 | Feature |  | Search a study with multiple parameters |  | New | XL | 120
90393 | User Story |  |  | Ability for global Study search using multiple parameters | New
90222 | User Story |  |  | View details about an existing project | New
90176 | Feature |  | Search Protocol(s) with multiple parameters |  | New | XXL | 160
90394 | User Story |  |  | Search for a specific Segment across all Projects using multiple parameters | New
90395 | User Story |  |  | See list of search results of the matching Segments and customize as necessary | New
90396 | User Story |  |  | Search for a specific Lane within a Segment or across projects using multiple parameters | New
90397 | User Story |  |  | See list of search results of the matching Lanes and customize as necessary | New
90085 | Epic | Integration |  |  | New | Core Build 1
90181 | Feature |  | Integrate with eMDM |  | New | XXL | 160
90183 | Feature |  | Integrate with Notification Engine |  | New
90184 | Feature |  | Integrate with TMS (By Directional) |  | New | XXL | 160
90185 | Feature |  | Integrate with WORLD-STAR (By Directional) |  | New | XXL | 160
90186 | Feature |  | Integrate with SSO |  | New | S | 40
93074 | Feature |  | Integrate with DW(orbis) |  | New | XL | 120
90087 | Epic | Audit Trail |  |  | New | Core Build 1
90190 | Feature |  | Record, Maintain and Track all the changes related to a Study/Protocol/Project |  | New | ORBIS; L | 80
90402 | User Story |  |  | Record, Maintain and Track the history of all the changes relates to a Study | New
90086 | Epic | Reports |  |  | New | Core Build 1
90187 | Feature |  | Generate CTL Reports |  | New | ORBIS; M; TMS; WORLD-STAR | 60
90399 | User Story |  |  | Generate CTL reports with multiple specifications | New
93119 | User Story |  |  | Ability to run DTP/CGT report | New
93121 | User Story |  |  | Run BioSphere report | New
93124 | User Story |  |  | Ability to run New Studies/Protocols report | New
90188 | Feature |  | Generate Sales Reports |  | New | ORBIS; M; TMS; WORLD-STAR | 60
90400 | User Story |  |  | Generate Sales reports with multiple specifications | New
93123 | User Story |  |  | Ability to run Sales report from Bio-STAR | New
90189 | Feature |  | TMS Reports |  | New | ORBIS; M; TMS | 60
90401 | User Story |  |  | Generate Customer reports with multiple specifications | New
93120 | User Story |  |  | Ability to run Transit Detail report from TMS | New
93993 | Epic | Data migration |  |  | New | Core Build 1
93995 | Feature |  | Data migration from WS Bio-STAR to New Bio-STAR |  | New | XXXL + XL | 320
99652 | Epic | Non-Functional Requirements |  |  | New | Core Build 1
99653 | Feature |  | Non-Functional Requirements |  | New | XXL | 160
4000
4200
S | 40
M | 60
L | 80
XL | 120
XXL | 160
XXXL | 200
M | 60
L | 80
XL | 120
XXL | 160
XXXL | 200

## Assumptions
Assumptions:
1 | Estimates: The effort-wise build estimates are high level estimates and rough order of magnitude as its scope and requirements has not been fully defined.
2 | Integration to legacy: There will be no World star integration testing. This piece is not factored and is beyond the scope of these estimates and also this project.
3 | Sourcing: The team size for this build will be with 1 onsite and 2 offshore developer resources. We are anticipating a turn- around time for such request as to anywhere between 1 and 2 weeks(max)
4 | Core team: Rajeev will be the architect with 50% allocation, Papri will be the Business Analyst 100% allocation, PM with 25% allocation and 3 developers (1 onsite/2offshore).
5 | Organization : The estimated hours and allocation for roles such as PM activities, QA testing, Transition management as per the Customer Portal project.
6 | Project Methodology: We will be following the Agile Scrum SAFE approach for software development with a standard 2 week iteration.
Integration : There are various integration points MDM, Mulesoft, World Star etc. and discovery was done based on the current state of these integration components
5 | Testing: UAT and Validation will go in parallel-so any UAT defects need to account for any impact to Validation-this might impact program go live date
6 | Security Testing: Security and Performance teams need to coordinate for execution
7 | Validation testing: Standard timeline for validated platforms is usually 2 weeks of execution time.
| Risks: | Category
1 | Estimates: These are high level estimates and we will deep dive into detailed requirements as we progress thru the project and may uncover more work for scope. The Contingency buffer will help mitigate this | Cost /Budget
2 | Sitecore: We currently don’t have any Sitecore developer or expertise inhouse in ABC/WC. Has not been easy to find a suitable resource in the market | Resource /Sourcing
3 | Sitecore: The request for infra structure and setup on the environment can have a delays and unknown dependencies. To mitigate this so may need to be scheduled with adequate lead time. | Schedule
Constraints
We have to have the project go live by Dec 2019.

## Cost_Salesforce
Task | No of hours | Total Cost | [9 empty] | SEC | 400
Salesforce User License |  | 84800 | [10 empty] | 400
Salesforce Shield |  | 34590
Build/Development | 4830 | 483000
Business Analyst | 1280 | 96000
Solution Architect | 640 | 91520
Testing | 1350 | 108000
Data warehouse | 400 | 42800
Security | 400 | 40000
Project Management |  | 35210 |  |  |  | Project/Program Management* | Hours | Rate | Dollar amount
Hypercare | 272 | 32826 |  |  |  | Wajahath Quraishi | 280 | 98 | 27440
|  | 1048746 |  |  |  | Scicley Christian | 70 | 111 | 7770
[6 empty] | Sudhir Reddy | 90 | 107 | 9630
Salesforce Platform | [5 empty] | Sahana Reddy | 420 | 111 | 46620
| Bio-Star Users with 5% growth | Salesforce Licensing fees for Bio-Star user | Salesforce Portal users (For Customer Service users) | Salesforce Shield Cost | Total Cost | Venu | 90 | 138 | 12420
|  |  |  | (20% of annual licensing cost of org. Which including 443 users ) |  | Jeannie | 90 | 138 | 12420
Year 1 | 200 | $264 X 200 =52,800 | 800 X $40 = $32,000 | 34590 | 1,20,390 | Lighton-Humphreys, Leslie | 40 | 107 | 4280
Year 2 | 210 | $264 X 210 = 55,440 | 840 X $40= $33,600 | 36320 |  | Jay Padmanathan | 90 | 143 | 12870
Year 3 | 222 | $264 X 222 = 58, 604 | 882 X $40 = $35,280 | [5 empty] | 35210
Year 4 | 233 | $264 X 233 = 61,512 | 927 X $40 = $37,080 |  |  | Hypercare*** | Hours | Rate | Dollar amount
Year 5 | 245 | $264 X 245 = 64,680 | 974 X $40 = $38,960 |  |  | Ruturaaj | 132 | 168 | 22176
[6 empty] | Jeff Rollins | 150 | 71 | 10650
[6 empty] | Dollar amount |  |  | 32826
[6 empty] | Testing** | Rate | Onsite (Hours) | Offshore (hours) | Rate | Dollar amount
[6 empty] | Functional Testing,E2E,Regression,Automation | 73 | 1580 | 1800 | 23.12 | $ 156,956
[6 empty] | Performance Testing | 85 | 120 | 495 | 23.12 | $ 21,644
[6 empty] | Validation Testing | 111 | 240 | 0 | 0 | $ 26,640
[6 empty] | Dollar amount |  |  |  |  | $ 205,240
Cost breakdown | No of hours | Rate | Total Cost
Build/Development | 4830 | 100 | 483000
Business Analyst | 960 | 75 | 72000
Architect | 480 | 143 | 68640
Testing** | 1350 | 80 | 108000
Datawarehouse | 400 | 107 | 42800
Security | 400 | 100 | 40000
Project Management* |  |  | 35210
Hypercare*** | 272 |  | 32826
| 9012 |  | 882476
Salesforce licensing cost | No of users | Cost per user | Total cost
user license New |  |  | 0
Current users |  |  | 0
Security shield |  |  | 0
Sales portal |  |  | 0

## Sheet1 (hidden)
Testing** | Hours | Rate | Dollar amount
Functional Testing | 900 | 58 | 52200
Performance Testing | 150 | 84 | 12600
Validation Testing | 240 | 111 | 26640
Penentration testing | 90 | 104 | 9360
Regression testing | 120 | 60 | 7200
108000

## Cost_Sitecore
Cost breakdown | No of hours | Rate | Total Cost |  | Testing** | Rate | Onsite (Hours) | Offshore (hours) | Rate | Dollar amount | SEC | 400
Build/Development | 5000 | 100 | 500000 |  | Functional Testing,E2E,Regression,Automation | 73 | 1580 | 1800 | 23.12 | $ 156,956 |  | 400
Business Analyst | 1280 | 75 | 72000 |  | Performance Testing | 85 | 120 | 495 | 23.12 | $ 21,644
Architect | 640 | 143 | 91520 |  | Validation Testing | 111 | 240 | 0 | 0 | $ 26,640
Testing** | 1350 | 80 | 108000 |  | Dollar amount |  |  |  |  | $ 205,240
Datawarehouse | 400 | 107 | 42800
Security | 400 | 100 | 40000
Project Management* | 350 |  | 35210
Hypercare*** | 272 |  | 32826
Infrastructure cost |  |  | Shared Infra |  | Hypercare*** | Hours | Rate | Dollar amount
Database setup cost | 100 | 107 | 10700 |  | Ruturaaj | 132 | 168 | 22176
Sitecore license cost (1st year) |  |  | 264000 |  | Jeff Rollins | 150 | 71 | 10650
Database license cost |  |  | 75000 |  | Dollar amount |  |  | 32826
1249176
[5 empty] | Project/Program Management* | Hours | Rate | Dollar amount
Site core Licensing Cost |  |  |  |  | Wajahath Quraishi | 280 | 98 | 27440
SiteCore Platform |  |  |  |  | Scicley Christian | 70 | 111 | 7770
| Users(5% growth) | Sitecore Licensing | SQL DB License | Total Cost | Sudhir Reddy | 90 | 107 | 9630
Year 1 | 1000 | 264000 | 75000 | 339000 | Sahana Reddy | 420 | 111 | 46620
Year 2 | 1050 | $42K | 0 | 42000 | Venu | 90 | 138 | 12420
Year 3 | 1103 | $42K | 0 | 42000 | Jeannie | 90 | 138 | 12420
Year 4 | 1159 | $42K | 0 | 42000 | Lighton-Humphreys, Leslie | 40 | 107 | 4280
Year 5 | 1217 | $42K | 0 | 42000 | Jay Padmanathan | 90 | 143 | 12870
35210
Cost breakdown | No of hours | Rate | Total Cost
Build/Development | 4600 | 100 | 460000
Business Analyst | 960 | 75 | 72000
Architect | 480 | 143 | 68640
Testing** | 1350 | 80 | 108000
Datawarehouse | 400 | 107 | 42800
Security | 400 | 100 | 40000
Project Management* | 350 |  | 35210
Hypercare*** | 272 |  | 32826
Infrastructure cost
Database setup cost
Sitecore license cost (1st year) |  |  | 264000
Database license cost |  |  | 75000
Addition lower enviroments (Dev/QA/Stage/Prod)
1198476
Sitecore licensing cost | No of users | Total cost
Database license | NA | 75000
Sitecore license | 1000 | 264000
Year 1 |  | 339000
Year 2 |  | 42000
Year 3 |  | 42000
Year 4 |  | 42000
Year 5 |  | 42000

## Salesforce Schedule
| HRS | Contingency (15%) | Onsite | Offsite | Iteration | No of Onsite resources | Number of Offshore | Total Combined capactity (per iteration) | No of development iterations | Testing ** (Performance/Validation/Regression/Penetration/End to End) | Hypercare(3 weeks)
BUILD | 4000 | 4600 | 960 | 1920 | 12 | 1 | 2 | 390 | 12 iterations | 1 iteration
**
Performance Testing
Validation Testing
Penentration testing
Regression testing